## Handover notes
Handover date | Handover type | Outgoing owner | Incoming owner | Client or project | Goal and context | Current status | Decisions and scope | Open question or risk | Action | Action owner | Due date | Status | Next touchpoint | Source or access notes
June 12 | Sales to customer success | Priya Shah | Sam Rivera | Northstar Design | Prepare weekly pipeline report with less manual copying | Discovery complete; sample workflow requested | Review sample June 18; no delivery date agreed | Lee to confirm if activity data can be exported | Send sample workflow | Priya Shah | June 14 | Open | June 18 call to review sample | Approved account workspace; assigned team only
June 12 | Shift change | Jordan Lee | Casey Morgan | Service desk evening queue | Keep urgent customer requests moving | Three tickets open; one waiting on customer | Escalate outage reports to duty lead | Confirm whether ticket 204 needs a callback | Review open queue and contact duty lead if outage | Casey Morgan | At shift start | Open | Check queue at 6 pm | Use approved ticketing system
June 12 | Project handover | Taylor Kim | Ravi Patel | Website content refresh | Complete approved page revisions | Drafts reviewed; two pages awaiting sign-off | Publish only after content owner approval | Confirm final image rights for page two | Request approval and verify image rights | Ravi Patel | June 16 | In progress | June 17 project check-in | Files in approved project folder
June 12 | Role change | Morgan Ellis | Alex Chen | Quarterly client review | Prepare review and agree next-quarter priorities | Data requested; meeting not yet scheduled | Client wants priorities discussed before dates are set | Confirm attendee list and data availability | Send scheduling options and request attendee list | Alex Chen | June 13 | Open | Set review after data arrives | Follow client-data handling policy
June 12 | Sales to service | Jamie Park | Avery Brooks | Pine Street Studio | Deliver the agreed onboarding workshop | Scope confirmed; intake form outstanding | One workshop; extra sessions need separate approval | Client to provide participant list | Send intake form and confirm workshop needs | Jamie Park | June 14 | Open | Workshop planning call June 19 | Approved client workspace